## Oranga Tamariki
Report | Report year | Findings by Monitor | Responses from Oranga Tamariki (Planned action) | Completion due date (provided by Oranga Tamariki) | Progress on actions (Not started, On track, Not on track, Complete, Discontinued) | Year ICM published action as complete [For ICM use only/not for publication]. | Comments (Oranga Tamariki) [Not for publication] | Column1
EoCA | 2020/2021 | Gaps in monitored agency data limits our ability to fully understand how they are meeting their obligations under the NCS Regulations. | Strengthen case file analysis |  | Complete | 2022/23
EoCA | 2020/2021 | Gaps in monitored agency data limits our ability to fully understand how they are meeting their obligations under the NCS Regulations. | Caregiver Information System (CGIS) to be implemented early 2022 |  | Complete | 2022/23
EoCA | 2020/2021 | Gaps in monitored agency data limits our ability to fully understand how they are meeting their obligations under the NCS Regulations. | Launch new whānau survey |  | Discontinued | 2022/23
EoCA | 2020/2021 | Gaps in monitored agency data limits our ability to fully understand how they are meeting their obligations under the NCS Regulations. | Explore replacement of CYRAS | Incremental release over 2024/25 and 2025/26 financial years | On track |  | It is accepted that ongoing work is required to ensure that data is robust and detailed. The Frontline Technology Systems Upgrade (FTSU) programme is working to replace legacy Ministry of Social Development systems that are outdated and no longer meeting the needs of frontline kaimahi. This work includes the digitisation of All About Me Plans. This will provide kaimahi with easier ways of recording information. The long-term approach will mean this information will be populated to other areas where we record tamariki and rangatahi information resulting in less duplication and increased accuracy of information. As we are working on significant changes, this will be a multi-year programme. We are currently working on a timeline to deliver our new frontline system that will replace CYRAS. As we shift our care and prevention responsibility to our partners, it is essential that we build systems for both internal and partnered kaimahi. These tools need to be responsive and adaptive to meet the needs of everyone involved so we can support better outcomes for tamariki, rangatahi, and their whānau or family group. In the 2023/24 financial year a prototype on All About Me Plans and integration software was developed. In May 2024, Oranga Tamariki received $62.5m in Budget, with this being held in tagged contingency pending Cabinet consideration of a Detailed Business Care. This is on track for September 2024 and would see us commence Tranche 1 of this multi-year programme. The first year would see the All About Me Plan released, and work commence on assessments and other plans for incremental release over the next two financial years
EoCA | 2020/2021 | Gaps in monitored agency data limits our ability to fully understand how they are meeting their obligations under the NCS Regulations. | Utilise Social Wellbeing Agency’s Data Exchange |  | Complete | 2022/23
EoCA | 2020/2021 | Self-monitoring of compliance with NCS Regulations needs to improve, so we can understand the quality of care and how to improve. | Full roll out of Whiti |  | Complete | 2022/23
EoCA | 2020/2021 | Self-monitoring of compliance with NCS Regulations needs to improve, so we can understand the quality of care and how to improve. | Use information from self-monitoring to implement policy and practice change | Completion date not provided | Not on track |  | No response from Oranga Tamariki
EoCA | 2020/2021 | Self-monitoring of compliance with NCS Regulations needs to improve, so we can understand the quality of care and how to improve. | Continue to develop self-monitoring measures | Completion date not provided | On track |  | No response from Oranga Tamariki
EoCA | 2021/2022 | Oranga Tamariki is yet to fulfil the regulatory requirement to self-monitor its compliance with the NCS Regulations. | Confirm self-monitoring framework, approach and model |  | Complete | 2023/24 | Significant work has been progressed to strengthen our self-monitoring of compliance with the NCS requirements to enable us to drive ongoing improvements in the quality of services and support for tamariki in care. We identified 16 lead indicators in 2022/23, and expanded these to 21 in 2023/24, to support our ongoing assessment of performance, and the foundational aspects of practice reflected in these lead indicators will be incorporated in the broader Oranga Tamariki performance system. Like our lead indicators the performance system is grounded in what rangatahi have told us is important to them. Our self-monitoring will be further strengthened with the performance system, which will include results and measures that connect what we do, how we are changing, and how we work with others to improve outcomes for tamariki and whānau. The performance system will be included in our new Strategic Intentions (to be published October 2024) and reported against in our 2024/25 Annual Report.
EoCA | 2021/2022 | Oranga Tamariki is yet to fulfil the regulatory requirement to self-monitor its compliance with the NCS Regulations. | Establish baselines and targets for measure identified |  | Complete | 2023/24 | A compliance framework was developed in 2022/23 to assess Oranga Tamariki performance against 16 lead indicators (expanded to 21 in 2023/24). This framework is used to show the indication of compliance and trajectory of compliance against each of the lead indicators. Baselines and targets for measures in the performance system will be established and reported in future accountability documents including our 2024/25 Annual Report. Measures will continue to be improved, including establishing baselines and targets, as the performance system is embedded over the next 1-2 years.
EoCA | 2021/2022 | Oranga Tamariki is yet to fulfil the regulatory requirement to self-monitor its compliance with the NCS Regulations. | Develop reporting of foundational measures at each assurance level |  | Complete | 2023/24 | Complementing the lead indicators, and while the performance system is being established, we are refining reporting at all levels. This includes at the site and regional level (through our Whiti tool) and new monthly reporting for Te Riu. This is supported by Te Riu quarterly deep dives into specific and priority areas of focus, which includes practice with tamariki in care. Additionally, we are developing new quarterly reporting to the Minister and public on key measures of strategic importance
EoCA | 2022/2023 | Oranga Tamariki is starting to improve data collection and monitoring | Implement programme of improvements to CGIS |  | Complete |  | The programme of improvements to CGIS has progressed well and we can provide data across a higher number of aspects of this performance. We have a few remaining areas of performance to report and focus on, and work will continue to enhance the system to enable this.
EoCA | 2020/2021 | Tamariki and rangatahi do not know and understand their rights | Strengthen feedback and complaints system |  | Complete |  | The Feedback and Complaints team continues to focus on improving the service provided to people who want to give Oranga Tamariki feedback. Ensuring our complaints service is accessible, relational and restorative has been and continues to be the focus. The Feedback and Complaints team work on enhancing quality assurance measures to enable greater consistency and quality in site lead complaint activity is continuing. The ability to record recommendations and the date they are implemented was rolled out as part of enhancements to the complaints system on 1 November 2023. Once this change has been embedded into complaint recording practice, Oranga Tamariki will be able to monitor and report on recommendations agreed and the date the recommendation was implemented. In the future this will enable further opportunities to give feedback on outcomes from formal complaint activity. A pilot survey to hear from people who have engaged with the complaints service is in development.
EoCA | 2020/2021 | Tamariki and rangatahi do not know and understand their rights | Create new resources with VOYCE [Manaaki Kōrero project] |  | Complete | 2023/24 | My Rights My Voice booklet and posters, and advocacy booklets and posters are available in all sites and residences. Some actions have been completed, with continued improvements ongoing.
EoCA | 2020/2021 | Tamariki and rangatahi do not know and understand their rights | Update “My Rights My Voice” resource |  | Complete | 2022/23
EoCA | 2020/2021 | Tamariki and rangatahi do not know and understand their rights | Mandate that rangatahi provided with grievance form after being searched or admitted to secure care units |  | Complete | 2023/24 | The Grievance process exists as an ‘opt in’ process for tamariki and rangatahi to ensure that they have the right to make a complaint, especially in the event of a search or admission to secure care. The Standard Operating Procedures that contain the grievance process and the means to raise a complaint is required to be provided to tamariki on admission, on a regular basis, and in a range of other means so all tamariki and rangatahi understand this is a fundamental right to raise their voice, at any time. Residences (Youth Justice and Care and Protection) have an emphasis on ensuring tamariki and rangatahi are aware of Whaia Te Maramatanga and the range of means they can seek support to raise any concerns. This includes many of the initiatives included in Manaaki Korero to improve the forms, and the means to ensure tamariki understand the role of advocates, as well as their right to make a complaint. This also aligns with the young person’s right to speak to their youth advocate or Council for Child. In accordance with the Residential Care Regulations, the legal representatives, site social workers, and whānau are informed of the secure care admission.
EoCA | 2020/2021 | Tamariki and rangatahi do not know and understand their rights | Appoint a National Quality Lead, Residential Quality Leads, National Training Coordinator, Residential Training Leads and Kaiwhakaako (cultural advisor within residence) |  | Complete | 2023/24 | Throughout the 2022/23 financial year, these roles have been implemented across the Care and Protection Residences. The National Quality Lead and National Training Lead are established and have been in place since 2022. There are two Quality Leads and two Residential Training Leads in place. There are also three Kaiwhakaako positions established. One of these positions is currently vacant. Youth Justice residences have Quality Leads established at each of their residences
EoCA | 2020/2021 | Tamariki and rangatahi do not know and understand their rights | Implement priority areas from Te Tohu o te Ora | This is an on-going action as each survey is finalised | On track |  | There is some work currently underway to address priority areas identified in Te Mātātaki 2023 (the report which presents the findings from Te Tohu o te Ora and organisational commitments). For example, a particular priority area is strengthening relationships with social workers, which has been addressed through the development and delivery of practice resources for social workers.
EoCA | 2021/2022 | To support tamariki and rangatahi to express their opinions, be involved in decisions, and share concerns, they need to know their rights. | Consider research insights and recommendations from rainbow and takatāpui rangatahi in care |  | Complete |  | A Rainbow Work Programme is being established in response to recommendations from the Making Ourselves Visible report and related research. This programme supports the organisational response to improve the response of Oranga Tamariki to the needs and experiences of tamariki and rangatahi who identify with rainbow and takatāpui communities. There is a strategic plan to progress the work and we are currently in phase one of this plan. There are three pieces of policy and guidance that feature in the report recommendations which centre on the interface between Oranga Tamariki and Health. These key pieces include Self Harm and Suicide, Sexual Health, and Consent for Health Services.
EoCA | 2021/2022 | To support tamariki and rangatahi to express their opinions, be involved in decisions, and share concerns, they need to know their rights. | Release Te Tohu o te Ora results early 2023 |  | Complete | 2022/23
EoCA | 2021/2022 | To support tamariki and rangatahi to express their opinions, be involved in decisions, and share concerns, they need to know their rights. | Establish another Youth Advisory Group |  | Complete | 2022/23
EoCA | 2021/2022 | To support tamariki and rangatahi to express their opinions, be involved in decisions, and share concerns, they need to know their rights. | Establish an ‘Advisor Rangatahi Voices’ |  | Complete | 2022/23
EoCA | 2021/2022 | To support tamariki and rangatahi to express their opinions, be involved in decisions, and share concerns, they need to know their rights. | Increase accessibility to information on rights |  | Complete | 2022/23
EoCA | 2022/2023 | Tamariki and rangatahi don't always know their rights or how to make a complaint | Pilot new “What’s Up” form at three residences (early 2024) |  | Complete | 2023/24
EoCA | 2022/2023 | Tamariki and rangatahi don't always know their rights or how to make a complaint | Pilot resources on making complaints (e.g. comic book) at four residences with full roll out in 2024 | 2025-06-01 | On track |  | Comic books have been developed and are being piloted in four residences. VOYCE will work with Oranga Tamariki on plans for roll out to other residences. Progress for the roll out plan and timeframe are currently slowed due to the organisational restructure.
EoCA | 2022/2023 | Tamariki and rangatahi don't always know their rights or how to make a complaint | Pilot voicemail complaints at three residences |  | Complete | 2023/24 | A voicemail complaints mechanism was piloted at one residence. The mechanism has not been rolled out across residences at this time due to feedback from the pilot. The pilot was useful to test a voicemail channel which to enable tamariki and rangatahi to lodge a grievance in a new way, removing some of the barriers if literacy was an issue. The evaluation of the pilot highlighted what went well, and what challenges occurred. The pilot has now ended. The next step is to take the learnings from the pilot and look more broadly at the end-to-end business processes for grievances, as well as the structure and staffing in residences to support this work more efficiently and effectively.
EoCA | 2022/2023 | Tamariki and rangatahi don't always know their rights or how to make a complaint | Implement new Standard Operating Procedure around grievances in 2024 | 2025-03-01 | On track |  | Grievance Standard Operating Procedures are under development and being aligned to the Draft National Investigator Training Module. This will be included in the Residences and Homes work programme.
EoCA | 2022/2023 | Tamariki and rangatahi don't always know their rights or how to make a complaint | Implement He Akoranga professional development to support disabled tamariki to be involved in decisions about them |  | Complete | 2023/24
EoCA | 2022/2023 | Tamariki and rangatahi don't always know their rights or how to make a complaint | Fund VOYCE Whakarongo Mai to provide advocacy and support for tamariki with significant communication needs |  | Complete | 2023/24 | The three year service agreement between Oranga Tamariki and VOYCE Whakarongo Mai concluded on 30 June 2024.
EoCA | 2022/2023 | Tamariki and rangatahi don't always know their rights or how to make a complaint | Incorporate complaints investigator training into Residences Workforce Development Strategy |  | On hold |  | The development of the module is currently on hold but will be incorporated into the Residences and Homes work programme.
EoCA | 2020/2021 | Connections with whānau and culture are important for tamariki and rangatahi Māori in care. | Further development of Te Toka Tūmoana (indigenous and bicultural principled framework) | 2025-12-01 | Delayed |  | Te Toka Tūmoana Practice Model is currently in trial as part of the suite of new models, tools, and resources within the Practice Approach and will be implemented nationally before the end of 2024. It has been transformed from a framework to an interactive practice model using Te Ao Māori principles to drive change through relational, inclusive, and restorative practice that will improve connections with whānau and culture for tamariki and rangatahi Māori in care.
EoCA | 2020/2021 | Connections with whānau and culture are important for tamariki and rangatahi Māori in care. | Update All About Me Plan policy to include emphasis on whānau searching |  | Complete | 2022/23
EoCA | 2020/2021 | Connections with whānau and culture are important for tamariki and rangatahi Māori in care. | With Whānau Care, recruit and support caregivers in partnership with iwi and kaupapa Māori providers |  | Complete | 2023/24 | Whānau Care have recruited and supported caregivers in partnership with iwi and kaupapa Māori Whanau Care is a care service delivered by 14 iwi and Māori partners. The 14 Whānau Care partners support a number of kin and non-kin caregivers under their model of care. This includes both caregivers recruited by the Whānau Care partner, and caregivers previously supported by Oranga Tamariki Caregiver Recruitment and Support who have transferred to be supported by the Whānau Care partner. As level 1 section 396 providers, Whānau Care can recruit, assess, and approve their own caregivers. As is the case for Oranga Tamariki, iwi and Māori care partners, and tauiwi care providers nationally, the recruitment of caregivers has proven challenging for Whānau Care partners. The Whānau Care partners will be consulted on the proposed Care Strategy which will inform the growth of Whānau Care into the future as part of the organisational reset
EoCA | 2020/2021 | Connections with whānau and culture are important for tamariki and rangatahi Māori in care. | Development of Te Hāpai Ō Māori cultural capability programme |  | Complete | 2022/23
EoCA | 2021/2022 | When staff lack cultural competence, relationships between Oranga Tamariki, whānau and other organisations can be negatively impacted. | Te Hāpai Ō baseline report to be completed in early 2023 |  | Complete | 2023/24
EoCA | 2021/2022 | When staff lack cultural competence, relationships between Oranga Tamariki, whānau and other organisations can be negatively impacted. | Te Hāpai Ō resources available on MyLearn |  | Complete | 2022/23
EoCA | 2021/2022 | When staff lack cultural competence, relationships between Oranga Tamariki, whānau and other organisations can be negatively impacted. | Second intake of Tū Māia |  | Complete | 2022/23
EoCA | 2021/2022 | When staff lack cultural competence, relationships between Oranga Tamariki, whānau and other organisations can be negatively impacted. | Refinement of Tū Māia (cultural capability programme) training resources |  | Complete | 2023/24
EoCA | 2021/2022 | When staff lack cultural competence, relationships between Oranga Tamariki, whānau and other organisations can be negatively impacted. | Commence Te Reo Māori strategy in 2023/24 financial year |  | On hold |  | Commencing the Te Reo Māori strategy was a planned action for the 2023/24 financial year. This work was placed on hold to focus on priorities for cultural capability at Oranga Tamariki led by Te Hāpai Ō, the Oranga Tamariki cultural capability team. Further consideration will be given to planning for the Te Reo Māori strategy in the 2024/25 financial year.
EoCA | 2020/2021 | Oranga Tamariki respond well when tamariki and rangatahi enter care; practices weaken during their time in care | Visit frequency changed to meet needs of tamariki |  | Complete | 2022/23
EoCA | 2020/2021 | Oranga Tamariki respond well when tamariki and rangatahi enter care; practices weaken during their time in care | Introduce “Tamariki in Care Clinics” (before June 2022) |  | Complete | 2022/23
EoCA | 2020/2021 | Oranga Tamariki respond well when tamariki and rangatahi enter care; practices weaken during their time in care | Facilitation of practice sessions by Practice Leaders that focus on NCS Regulations |  | Complete | 2022/23
EoCA | 2022/2023 | Fewer rangatahi leaving care are being supported | Include transition support data/Transitions page in Whiti |  | Complete | 2023/24 | Care and Protection and Youth Justice transitions data has been included in Whiti at site and regional level pages. Online training sessions are on-going
EoCA | 2022/2023 | Fewer rangatahi leaving care are being supported | Implement new functionality for recording life skills assessments and transition planning on CYRAS |  | Complete | 2023/24 | CYRAS functionality has been added and a CYRAS guide created to support kaimahi in recording accurately. This will continue to be reinforced through training to implement the new life skills assessment tool.
EoCA | 2022/2023 | Fewer rangatahi leaving care are being supported | Provide targeted assistance and training to lower performing regions |  | Complete |  | In Tāmaki Makaurau, there has been a meeting with the regional leadership teams, and two full days of training with approximately 80 attendees across the region. Online training has been started with the East Coast
EoCA | 2022/2023 | Fewer rangatahi leaving care are being supported | Introduce letter of entitlement for rangatahi prior to leaving care | 2025-02-01 | On track |  | A letter of entitlement has been piloted with 17.5-year-olds. A key finding was that the letter needs to be introduced earlier due to eligible rangatahi being discharged prior to this age. We are working towards having these letters go out to all rangatahi eligible for transition support services (from 15 years onwards) alongside direct contact to social workers of eligible rangatahi at 15, 16 and 17 years of age to support them in carrying out their transition obligations
EoCA | 2020/2021 | Caregivers need more support | Monitor caregivers’ participation in ‘Prepare to Care’ programme |  | Complete | 2022/23
EoCA | 2020/2021 | Caregivers need more support | Identify number of caregivers who have participated in trauma-informed learning/support programmes |  | Complete | 2022/23
EoCA | 2020/2021 | Caregivers need more support | Conduct case file review to improve support to caregivers |  | Complete | 2022/23 | Since this action was established, case file analysis of care has significantly strengthened. It now includes routine oversight of a selection of core aspects of caregiver support practice. Caregiver Support and Recruitment Services (CGRS) also monitor the quality of caregiver support, alongside caregiver assessment and review practice, each quarter using the Quality Practice Tool process.
EoCA | 2020/2021 | Caregivers need more support | Reform the system of financial assistance and support for caregivers | Phase one will be complete by the end of Quarter 2 2024/25 financial year | On track |  | We have drafted a programme of work which focuses on improving the experiences of caregivers by strengthening existing practice, policies and processes. The programme will sit alongside work to develop a National Care Strategy to set an overarching and strategic approach for how we deliver care.
EoCA | 2021/2022 | Caregivers continue to tell us that they need more support | Continue to listen to caregivers’ voices about their experiences | Phase one will be complete by the end of Quarter 2 2024/25 financial year | On track |  | Pulse surveys are being planned to measure progress. A Corrective Action Plan in response to the 2023 Caregiver Satisfaction survey is currently under development and will be focusing on the following areas: Maintaining and improving respect for caregivers including recognition of learning and service by caregivers, Working with the Privacy Team to help kaimahi understand what information can be shared with caregivers and Making information about tamariki and rangatahi health needs accessible on the KidsHealth website.
EoCA | 2021/2022 | Caregivers continue to tell us that they need more support | Explore unfulfilled support themes reported | Phase one will be complete by the end of Quarter 2 2024/25 financial year | On track |  | Themes include a lack of communication and support, not providing guidance, not responding to requests for help or missing appointments, not being listened to when sharing their views and opinions. This has made caregivers feel undervalued and taken for granted. The Corrective Action Plan outlined above will contribute to measures to address themes. Findings from the Caregiver Satisfaction Survey will be shared with kaimahi to increase understanding of caregiver needs
EoCA | 2020/2021 | Agency support of health needs, especially mental health needs, is variable. | Case file analysis to capture diagnosis type to provide greater insight into disability needs for tamariki and rangatahi in care |  | Complete | 2022/23
EoCA | 2020/2021 | Agency support of health needs, especially mental health needs, is variable. | Establish inter-agency governance group across residences |  | Complete | 2023/24 | Six Te Whatu Ora Districts have been providing (or subcontracting) co-located health services for Oranga Tamariki’s care and protection and youth residences since 2012. To improve health service provision and collaboration between Oranga Tamariki and the local health and mental health agencies, interagency managers groups have been established across four regions to meet the needs of residences within Counties Manukau, Mid Central/Capital Coast, Hutt Valley/Capital Coast and Otago/Southern districts. In 2022, Te Whatu Ora budget successfully allocated funding to enhance the provision of specialist mental health services to tamariki and rangatahi in Oranga Tamariki care and protection residences. This funding was specifically targeted at ensuring the appropriate level of mental health support is provided to complement the in-reach services already received.
EoCA | 2021/2022 | The prevalence of disability among tamariki and rangatahi in care is not well understood. | Improve disability data prevalence measurement |  | Complete | 2023/24 | Oranga Tamariki has focused on working with data more effectively. We have reviewed how we use data to sharpen our prevalence data and have looked at how we can use Gateway Assessment data better.
EoCA | 2021/2022 | The prevalence of disability among tamariki and rangatahi in care is not well understood. | Examine experiences of tamariki and rangatahi in care receiving Disability Support Services | To be determined | On track |  | Oranga Tamariki is currently undertaking a research and data project focused on understanding the purchasing of specialist residential services for Disability Support Service eligible tamariki and rangatahi with the highest support needs, and whether the expected outcomes are being achieved.
EoCA | 2021/2022 | The prevalence of disability among tamariki and rangatahi in care is not well understood. | Six-to-eighteen month focus on disability data improvements |  | Complete | 2023/24 | Disability data improvements remain a focus and how we can use data more effectively. The Frontline Technology Systems Upgrade will also help us to improve how we gather disability data.
EoCA | 2021/2022 | The prevalence of disability among tamariki and rangatahi in care is not well understood. | Disability Advisory Group provide advice on Disability Strategy |  | Complete | 2023/24 | The Disability Advisory Group was established in October 2022. The Disability Advisory Group worked together to create the Disability Strategy, which was approved by Te Riu in September 2023.
EoCA | 2021/2022 | Lack of availability and access to mental health services continues to be a barrier. | Work with other children’s agencies through OTAP to improve access to services to meet identified need | This is a cross-government work programme and is subject to Ministerial priorities. The Minister is due to report back to Cabinet on implementation by June 2025. | On track |  | The Minister for Children has approved a small number of focus areas for the Oranga Tamariki Action Plan to be delivered over the next 6-18 months. These focus areas supersede the cross-agency plans that were approved by the Social Well-Being Board in 2023. Under the Health focus areas, agencies will be progressing a redesign of the Gateway service and enhancing visibility of children in care in the health system. Oranga Tamariki will be working alongside Health agencies to develop and implement a cross-government mental health work programme which sits outside the focus areas for the Action Plan. This includes review of the Mental Health Act and strengthening services for child and youth mental health. Operationally, Oranga Tamariki is also working to enhance mental health supports in residences in conjunction with Health agencies. Implementation details are still yet to be finalised
EoCA | 2022/2023 | Access to health services continues to be a barrier. | Improve kaimahi understanding of health and disability needs | The second phase of implementation will begin in 2025. | On track |  | First phase: Completed. Oranga Tamariki and Health New Zealand have worked with KidsHealth to give frontline kaimahi and caregivers access to health and wellbeing guidance through the Oranga Tamariki Practice Centre. Caregiver Social Workers will introduce caregivers to the information through a regular visit and support them to access it via a QR code. Caregiver Social Workers will gather feedback from caregivers, including identifying additional health and wellbeing guidance that caregivers would find useful. KidsHealth are supportive of developing further health and well-being content where needed. This is the first phase of the development guidance under the health focus areas under the Oranga Tamariki Action Plan. Second phase: In progress. Additional guidance will be developed to support the redesigned Gateway service and enhanced visibility of children in care within the health system. This will include guidance for frontline health professionals and Oranga Tamariki kaimahi.
EoCA | 2022/2023 | Access to health services continues to be a barrier. | Develop kaimahi knowledge and capability through the Disability Strategy | On-going from July 2024 | On track |  | We are currently considering awareness raising opportunities to support frontline care and protection and youth justice kaimahi on disability training in induction for new recruits and working with the Practice Approach to include disability in Learning Cycle 4. A programme of work informed by the Disability Strategy commenced in July 2024 to create a core competency framework for disability knowledge. The framework will inform subsequent capability development plans for Oranga Tamariki kaimahi. Ongoing activity to raise disability awareness and knowledge among frontline kaimahi, include: Six Puawai (social worker induction programme) training sessions, Presentation on disability, neurodiversity and the use of communication and behavioural tools delivered to youth justice residence kaimahi, Disability awareness training, as required, in residences and Two “Altogether Autism webinars” scheduled to run in August 2024
EoCA | 2022/2023 | Access to health services continues to be a barrier. | Review self-harm and suicide guidance and consider improvements to reporting | 2026-06-01 | On track |  | Oranga Tamariki is in the process of scoping a full review of our self-harm and suicide guidance. The review activities will include: Aligning the guidance with our practice framework and approach, Reviewing the practice tools we use - Substance Abuse Assessment (SACS), Kessler and Suicide screen and part of the review will consider contemporary best practice and whether these remain the most appropriate tools. Evaluate the Towards Wellbeing programme, delivered by Clinical Advisory Services Aotearoa (CASA), and provides support and advice to social workers working with tamariki and rangatahi with suicide risks. Hearing the voices of rainbow and other rangatahi groups, caregivers and social workers.
EoCA | 2022/2023 | Access to health services continues to be a barrier. | Review ‘Supporting Parents, Healthy Children’ guidance for parents with mental health and addictions [led by Health] |  | Complete |  | Whāraurau will publish guidance on their website. This will make it easier for social workers and practitioners to navigate to practical tips, online learning opportunities, and other resources. The content will be updated as required. We will have the opportunity to review the content before the website goes live. Our own guidance will then be adjusted to add links to the Whāraurau website.
EoCA | 2022/2023 | Access to health services continues to be a barrier. | Review ‘Let’s Get Real’ framework [led by Health] |  | Complete |  | This is a framework for mental health clinicians and practitioners. We are continuing to contribute to the review of the framework as it applies to Infant, Child and Adolescent Mental Health Services (ICAMHS).
EoCA | 2022/2023 | Access to education support continues to be a challenge. | Finalise processes around data sharing on school attendance with Ministry of Education |  | Complete | 2023/24 | Oranga Tamariki and Ministry of Education have finalised an information sharing agreement and associated detailed data agreements. These data shares will contain data regarding school enrolment, attendance and engagement (standdowns, suspensions, expulsions and exclusions). Data shares have begun mid-August 2024 after the agreement was signed of
EoCA | 2022/2023 | Access to education support continues to be a challenge. | Focus on improving attendance and supporting tamariki to re-engage in education, through the Lead Education Advisor for Children in Care |  | Complete | 2023/24 | An Education Attendance Data Working Group has been established within Oranga Tamariki to support this workstream and any operational changes required. Access to this data allows Oranga Tamariki to support tamariki and rangatahi to be enrolled at, and regularly attending and achieving in education.
EoCA | 2020/2021 | Agencies not communicating and working together effectively is a common barrier to achieving outcomes. | Action Plan to be published early 2022 |  | Complete | 2022/23
EoCA | 2020/2021 | Agencies not communicating and working together effectively is a common barrier to achieving outcomes. | Ngā Tini Whetū (collaboration between Oranga Tamariki, Te Puni Kōkiri, ACC and Whānau Ora Commissioning Agency) to develop and implement a new whānau-centred early-intervention prototype |  | Complete | 2023/24 | Oranga Tamariki have ceased financial support of Ngā Tini Whetū but remain supportive of the initiative and are connected to Ngā Tini Whetū through our strategic partnership with Te Whānau o Waipareira Trust
EoCA | 2020/2021 | Agencies not communicating and working together effectively is a common barrier to achieving outcomes. | Develop new schedule in MoU between Oranga Tamariki, Police, Ministry of Health and Health New Zealand |  | Complete | 2022/23
EoCA | 2021/2022 | Connections between Oranga Tamariki, health and education providers and communities remain splintered. | Work with the Regional Public Service Commissioners to drive support and engagement in OTAP | Completion date not provided | On track |  | The Oranga Tamariki Action Plan six-monthly implementation report for the period of July to December 2023 has been endorsed by the Child and Youth Ministerial Group and has been published on the Oranga Tamariki Action Plan website. Oranga Tamariki have been working with the Regional Public Service team and supporting the Regional Commissioners who are committed to supported the Oranga Tamariki Action Plan in their respective regions. Engagement with Regional Public Service Commissioners has been focused on the Government Targets for Reducing Serious and Persistent Youth Offending. There will be consideration of whether regional governance bodies led by Regional Public Service Commissioners could be utilised to support both the Government Targets and Oranga Tamariki Action Plan.
EoCA | 2021/2022 | Connections between Oranga Tamariki, health and education providers and communities remain splintered. | Progress next set of in-depth assessments and provide agency responses |  | Complete | 2023/24 | Cross-agency responses to the 2022 in-depth assessments have been published and three additional in-depth needs assessment have been published and three additional in-depth needs assessment were completed in 2023. All in-depth needs assessments have been delivered. Early risk needs assessments are still to be delivered. The Oranga Tamariki Action Plan six-monthly implementation report for the period of July to December 2024 has been endorsed by the Child and Youth Ministerial Group and have been published on the Oranga Tamariki Action Plan website.
EoCA | 2022/2023 | Collaboration and information sharing between government agencies remains a barrier. | Complete implementation of the OTAP |  | Complete | 2023/24 | As mentioned above, an information sharing agreement has been finalised between Oranga Tamariki and Ministry of Education to support the sharing of data relating to school enrolment, attendance and engagement. Oranga Tamariki and Health agencies have developed an information sharing agreement and are currently exploring options to improve the health system visibility of care status so that when tamariki and rangatahi interact with the health system such as general practitioners, the health system will identify their care status to enable more responsive care from practitioners and to ensure they receive the appropriate supports and services to meet their health needs. Additional information share requirements are being considered and will inform the development of further information sharing agreements.
EoCA | 2021/2022 | For social workers to successfully perform their role they need to be able to spend more time with tamariki, rangatahi, whānau, caregivers and communities. | Development of an organisational demand and allocation model, implemented in 2022/23 financial year | 2025-04-01 | On track |  | We have developed a prototype case complexity statistical model and have used it to assess the range of complexity. A report is currently being prepared on the interpretation of the findings. The report and analysis are currently being prepared.
EoCA | 2021/2022 | For social workers to successfully perform their role they need to be able to spend more time with tamariki, rangatahi, whānau, caregivers and communities. | Office of the Chief Social Worker will focus on better understanding social worker capacity, caseload complexity and workload management | 2024-09-01 | Not on track |  | We have developed a prototype case complexity statistical model and have used it to assess the range of complexity. A report is currently being prepared on the interpretation of the findings. Work has been undertaken to estimate optimal caseload/workload sizing for care and protection social workers. To better understand the demand on social workers’ time, a Time in Motion Study commenced in early 2024, this work has been paused and will be considered at a later date.
EoCA | 2021/2022 | For social workers to successfully perform their role they need to be able to spend more time with tamariki, rangatahi, whānau, caregivers and communities. | Streamline core processes and tasks to prioritise social workers’ time with tamariki, rangatahi, whānau and caregivers |  | Complete | 2023/24 | We have validated a core task list for social workers across Services for Children and Families and Youth Justice. This work supports workforce diversification and increasing the scope of what tasks roles such as Allied Support Workers can undertake. Broadening our approach to the practice workforce is necessary to free up social workers time, and concurrently better meeting the wider needs of tamariki and whānau.
EoCA | 2021/2022 | For social workers to successfully perform their role they need to be able to spend more time with tamariki, rangatahi, whānau, caregivers and communities. | Development of a supervision strategy |  | Complete | 2023/24 | We have developed an Enhancing Supervision Strategy. It is anticipated key components of the strategy will be incorporated into the future Oranga Tamariki structure. The Enhancing Supervision Strategy responds to the practice environment in which practitioners work. It will support the right supervision offer for all practitioners, not just social workers.
EoCA | 2021/2022 | For social workers to successfully perform their role they need to be able to spend more time with tamariki, rangatahi, whānau, caregivers and communities. | Invest further in supervisors’ ability to support social work practice | To be determined | Not on track |  | A new Tangata Whenua and Bicultural supervision model will be implemented as part of Learning Cycle 3. Work is continuing to develop an Enhancing Supervision Strategy. It is anticipated that key components of the strategy will be incorporated into the future structure of Oranga Tamariki.
EoCA | 2022/2023 | Social workers are not able to see tamariki and rangatahi as often as they need. | Produce tools to support engagement with tamariki and rangatahi [HUIA Publishing, early 2024] |  | Complete | 2023/24 | Resources to support social worker engagement practice with tamariki and rangatahi are being distributed through existing learning and development channels including induction, He Akoranga and Learning Cycle 3 for the practice approach.
EoCA | 2021/2022 | Oranga Tamariki is not always assessing caregivers and their households before tamariki and rangatahi are placed with them. | Determine why assessment and approval is not occurring |  | Complete | 2023/24 | Caregivers are not able to be approved if they do not meet the safety check and/or assessment criteria, however, at times tamariki are already placed with them as part of a Provisional Approval process. Caregiver periodic reviews are not being completed on time, which can mean that the status of these caregivers is shifting to unapproved”. This can be a result of difficulty engaging with caregivers.
EoCA | 2021/2022 | Oranga Tamariki is not always assessing caregivers and their households before tamariki and rangatahi are placed with them. | Office of the Chief Social Worker to implement practice guidance around provisional approval |  | Complete | 2023/24 | There is Practice Guidance available for all kaimahi on the Practice Centre regarding Provisional Approvals. Caregiver Recruitment Support Services (CGRS) kaimahi receive coaching from the CGRS Practice Advisors about Provisional Approvals. There is an expectation that CGRS lead in the Provisional Approval space, and that Supervisors and CGRS Managers monitor that that this occurs in their regions. Should a Provisional Approval need to be escalated to Manager level for approval, CGRS Practice Advisors support the region to ensure that the process is followed correctly.
Returning Home From Care | 2023-05-01 | Guidance on the removal of custody orders, and use of coercive powers, is unclear. | Develop new policy guidance for kaimahi working to return tamariki to their parent or usual caregivers | 2024-09-01 | On track |  | Work is nearing completion on the return home policy and guidance. These address the need for planning for the discharge of custody orders as part of the return home process
Returning Home From Care | 2023-05-01 | Data on the success of tamariki returning home is limited. | Upgrade Frontline Technology Systems to improve data | Incremental release over 2024/25 and 2025/26 financial years | On track |  | It is accepted that ongoing work is required to ensure that data is robust and detailed. The Frontline Technology Systems Upgrade (FTSU) programme is working to replace legacy Ministry of Social Development systems that are outdated and no longer meeting the needs of frontline kaimahi. This work includes the digitisation of All About Me Plans. This will provide kaimahi with easier ways of recording information. The long-term approach will mean this information will be populated to other areas where we record tamariki and rangatahi information resulting in less duplication and increased accuracy of information. As we are working on significant changes, this will be a multi-year programme. We are currently working on a timeline to deliver our new frontline system that will replace CYRAS. As we shift our care and prevention responsibility to our partners, it is essential that we build systems for both internal and partnered kaimahi. These tools need to be responsible and adaptive to meet the needs of everyone involved so we can support better outcomes for tamariki, rangatahi, and their whānau or family group. The last financial year enabled prototyping on All About Me Plans and integration software. In May 2024, Oranga Tamariki received $62.5m in Budget, with this being half in tagged contingency pending Cabinet Consideration of a Detailed Business [Case]. This is on track for September 2024 and would see us commence Tranche 1 of this multi-year programme. The first year would see the All About Me Plan released, and work commence on assessments and other plans for incremental release over the next two financial years.
Returning Home From Care | 2023-05-01 | Data on the success of tamariki returning home is limited. | Undertake case file analysis on a sample of cases where tamariki have been returned home |  | On track |  | Our routine Care Standards case file analysis each year includes a sample of tamariki with a new Return Home placement over the review period. Out forward work programme includes further work to understand those situations in which tamariki have successfully returned home to their parents/usual carers, to enable learnings to be incorporated into further continuous improvement activities.
Returning Home From Care | 2023-05-01 | Data on the success of tamariki returning home is limited. | Prioritise supporting communities – e.g., work with Māori, Iwi and community partners to support the discharge of custody orders |  | Complete |  | Each region is working with the Permanent Caregiver Support Services (PCSS) on permanency planning, training and support. Regions have engaged Open Home Foundation (OHF) who have permanency workers, experiences in return home. OHF assist our social workers, and whānau to navigate through the court process and care arrangements to achieve permanency.
Returning Home From Care | 2023-05-01 | Data on the success of tamariki returning home is limited. | Engage with the judiciary and counsel to improve collaborative practice |  | Complete |  | We have utilised court liaison meetings to report on progress, seek shared decisions around barriers and maintain an ongoing focus. This work has now been embedded and is considered BAU.
Returning Home From Care | 2023-05-01 | Data on the success of tamariki returning home is limited. | Prioritise support to parents and whānau (intensive support services with partners) |  | Complete |  | Open Home Foundation currently has the largest contract to support Oranga Tamariki with permanency work. However, over the last five years, more agencies, particularly iwi and Māori agencies have shown an interest in supporting 'return home' or 'remain home' placements with the intent to move to support orders before discharging all orders. This is a work in progress that involves the participation of the Family Court. Some of our partners, specifically Waikato Tainui and Waitomo Papakainga, are actively engaged in promoting community participation for the discharge of orders thorough Te Ao Marama, and initiative through the Justice system. TO date, we have supported partners through the Intensive Intervention function to play a more supportive role.
Returning Home From Care | 2023-05-01 | Data on the success of tamariki returning home is limited. | Enhance processes to identify tamariki with a clear and safe pathway to exit custody. |  | Complete |  | A move to permanency by discharging orders has always been a priority for Oranga Tamariki. We have identified mechanisms that make family or whānau, or return/remain home care arrangements visible at Site and Regional levels. We have established regular monitoring by regions of tamariki and rangatahi in family or whānau or return home care arrangements. We have identified tamariki and rangatahi who we can now move to permanency. Sites and regions have developed processes to identify tamariki and rangatahi who have been in long term stable homes with whānau where there is potential to establish permanency and discharge custody orders.
Returning Home From Care | 2023-05-01 | While planning is important to the success of a return home, almost half of returns home are unplanned. | Develop new policy and supporting guidance related to return home | 2024-09-01 | On track |  | Work is nearing completion on the return home policy and guidance. The policy requires planning prior to the return home. It addresses unexpected returns home and requires the policy to be applied in these circumstances.
Returning Home From Care | 2023-05-01 | While planning is important to the success of a return home, almost half of returns home are unplanned. | Develop guidance to strengthen tamariki and rangatahi involvement in decisions (e.g. revised ‘My Rights. My Voice’ booklet) | 2024-09-01 | On track |  | As mentioned above, work is nearing completion on the return home policy and guidance. Tamariki and rangatahi involvement in the return home planning and decision-making process is reinforced within the policy and guidance. My Rights My Voice booklet and posters, and advocacy booklets and posters are available in all sites and residences.
Returning Home From Care | 2023-05-01 | Tamariki who have returned home are not visited in the first month as the policy recommends. | Develop case complexity model to help workforce planning and resource allocation [testing and refinements to occur in September 2023] |  | Not on track |  | A prototype case complexity statistical model has been developed and is being further considered to assess the range of complexity. A report is currently being prepared of the findings. Work has been completed to better understand the roles and responsibilities of statutory social work and the implications of legislation, policy, organisational delegations and professional obligations. This work is completed and is a key input into the Social Work workforce strategy
Returning Home From Care | 2023-05-01 | Tamariki who have returned home are not visited in the first month as the policy recommends. | Implement new QPT to assess quality of return home process, to include a focus on social workers visiting children who have returned home |  | Complete |  | Return home QPT was completed in November 2023.
Returning Home From Care | 2023-05-01 | Tamariki who have returned home are not visited in the first month as the policy recommends. | Review ‘Returning tamariki to parents, family or whānau’ work programme |  | Complete |  | We have identified mechanisms that make family or whānau, or return/remain home care arrangements visible at Site and Regional level. We have established regular monitoring by regions of tamariki and rangatahi in family or whānau or return home care arrangements. We have identified tamariki and rangatahi who we can now move to permanency. Sites and regions have developed processes to identify tamariki and rangatahi who have been in long term stable homes with whānau where there is potential to establish permanency and discharge custody orders. This work has now been embedded and is considered BAU.
Returning Home From Care | 2023-05-01 | Support from the wider social sector is varied, with communication, collaboration and funding being barriers to success. | Work with Regional Public Service Commissioners to drive regional solutions | Ongoing | In progress |  | The Oranga Tamariki Action Plan six-monthly implementation report for the period of July to December 2023 has been endorsed by the Child and Youth Ministerial Group and has been published on the Oranga Tamariki Action Plan website. Oranga Tamariki have been working with the Regional Public Service team and supporting the Regional Commissioners who are committed to support the Oranga Tamariki Action Plan in their respective regions. Engagement with Regional Public Service Commissioners have been focused on the Government Targets for Reducing Serious and Persistent Youth Offending. There will be consideration of whether regional governance bodies led by Regional Public Service Commissioners could be utilised to support both the Government Targets and Oranga Tamariki Action Plan.
Returning Home From Care | 2023-05-01 | Support from the wider social sector is varied, with communication, collaboration and funding being barriers to success. | Deliver the Oranga Tamariki Action Plan | Ongoing | On track |  | We have delivered on Actions 3 and 4 of the Oranga Tamariki Action Plan. Through the completion of Action 3, we have in depth understanding of the systems gaps in Education, Health and Housing. This information has then been used to inform the Action Plan Focus Areas for the next 6-18 months as agreed by Ministers. A small number of priority areas have been established, focused on improving key health, education and housing outcomes for tamariki and rangatahi in care, supported by improved data an information sharing practices across all three areas. The Gateway review has been completed. Along with development of health and wellbeing guidance for caregivers and frontline kaimahi.
Returning Home From Care | 2023-05-01 | Inconsistent government policies and practice is a barrier to a successful return home. | Report to Oranga Tamariki Ministerial Board by 30 November 2023 on a range of Oranga Tamariki matters, including effectiveness of legal provisions related to tamariki and rangatahi returning home |  | Complete |  | The original commitment from Oranga Tamariki to the Independent Children's Monitor's 'Returning Home From Care' report was that "The Oranga Tamariki Ministerial Advisory Board will deliver a report to the Minister by 30 November 2023" on a range of matters. The Ministerial Board (the Board) provided Oranga Tamariki with their report in March 2024. The report has since been provided to the Minister for Children who has acknowledged the work of the Board and thanked them for the report.
Access to Primary Health Services and Dental Care | 2023-11-01 | There is a lack of clarity regarding what the NCS Regulations require and how they can be achieved. | Review the Gateway Assessment process |  | Complete |  | The Gateway Assessment Review has been completed and the Minister for Children, Health, and Education have approved its findings and recommendations of six key changes for a redesigned Gateway service. These changes would shift the service from a one-off, specialist-oriented approach to one that has an increased and ongoing role for primary healthcare, partners and providers, with regular review and ongoing support provided in a seamless and integrated way where children and whānau/family are at the centre of decision-making. A clearer accountability framework and strengthened governance will support these changes. We have redeveloped a cross-agency plan for the Gateway redesign phase based on the recommendations.
Access to Primary Health Services and Dental Care | 2023-11-01 | There is a lack of clarity regarding what the NCS Regulations require and how they can be achieved. | Review guidance related to healthcare, with a focus on consent | 2024-10-01 | On track |  | Our practice guidance is being updated to ensure clarity on the situations where consent is required when medical or dental examination and treatment is being considered, including after-hours/emergencies; we have also strengthen it in line with our practice approach. The updated guidance is currently at the final approval stage.
Access to Primary Health Services and Dental Care | 2023-11-01 | There is a lack of clarity regarding what the NCS Regulations require and how they can be achieved. | Joint work with health agencies on the Health Response Framework |  | Complete |  | The Gateway Assessment Review has been completed and the Minsiters for Children, Health, and Education have approved its findings and recommendations of six key changes for a redesigned Gateway service. These changes would shift the service from a one-off, specialist-oriented approach to one that has an increased and ongoing role for primary healthcare, partners and providers, with regular review and ongoing support provided in a seamless and integrated way where children and whānau/family are at the centre of decision-making. A clearer accountability framework and strengthened governance will support these changes. We have developed a cross-agency plan for the Gateway redesigned phased based on the recommendations. An information sharing agreement is also being finalised between Oranga Tamariki and Ministry of Education to support the sharing of data relating to school enrolment, attendance and engagement. Oranga Tamariki and Health agencies are developing an information sharing agreement and are currently exploring options to improve health system visibility of care status so that when children and young people interact with the health system such as general practitioners, the health systems will identify their care status to enable more responsibe care form practitioners and to ensure they receive the appropriate supports and services to meet their additional needs. Additional information sharing requirements are being considered and will inform the development of future information sharing agreements.
Access to Primary Health Services and Dental Care | 2023-11-01 | There is a lack of clarity regarding what the NCS Regulations require and how they can be achieved. | Consider whether the NCS Regulations remain fit for purpose | 2026-12-01 | On track |  | This will be considered, under current legislation, this must be completed by 2026.
Access to Primary Health Services and Dental Care | 2023-11-01 | There is a lack of clarity regarding what the NCS Regulations require and how they can be achieved. | Develop a clinical tool for primary health practitioners to support annual health assessments | On hold | Not on track |  | Te Whatu Ora are intending to develop a commissioning process shortly.
Access to Primary Health Services and Dental Care | 2023-11-01 | Policies and guidance are unclear, resulting in inconsistencies around caregiver responsibilities and health-related information being shared. | Embed practice guidance through ‘Learning Cycles’ [Cycle Three due in 2024] | 2024-12-01 | On track |  | A phased caregiver work programme is under development that will support inconsistencies around caregiver responsibilities and health-related information being shared. The intention is to develop a framework that clarifies when a child comes into care and how we will clarify with parents and guardians how day to day decisions will be made for the individual child and reflected in the child's caregiver's plans, including health and dental decisions.
| 2023-11-01 | Policies and guidance are unclear, resulting in inconsistencies around caregiver responsibilities and health-related information being shared. | Review practice guidance to reflect the health needs of tamariki and rangatahi | 2024-12-01 | In progress |  | Policy and guidance related to Health and Dental support for tamariki and rangatahi in care or custody has been reviewed, updated and clarified.
Access to Primary Health Services and Dental Care | 2023-11-01 | Policies and guidance are unclear, resulting in inconsistencies around caregiver responsibilities and health-related information being shared. | Design additional resources for social workers to share with caregivers to support enrolments |  | Complete |  | Caregivers and kaimahi have been made aware of the KidsHealth website and have been provided with details for access. Individual and unique health needs of tamariki and rangatahi are identified and supported as required and recorded in the Caregiver Support Plan.
Access to Primary Health Services and Dental Care | 2023-11-01 | Caregivers are not well supported to ensure that tamariki and rangatahi health needs are met | Review guidance (as above) to clarify expectations of staff relating to primary health services and dental care | 2024-12-01 | On track |  | Policy and guidance related to Health and Dental support for tamariki and rangatahi in care or custody has been reviewed, updated and clarified.
Access to Primary Health Services and Dental Care | 2023-11-01 | Caregivers are not well supported to ensure that tamariki and rangatahi health needs are met | Develop a central website on health information (for tamariki and rangatahi in care) for social workers and caregivers [OTAP] |  | Complete |  | Oranga Tamariki and Health New Zealand have worked with Kids Health to give frontline kaimahi and caregivers access to health and wellbeing guidance through the Oranga Tamariki Practice Centre. Caregiver Social Workers will introduce caregivers to the information during regular visits and support them to access it via a QR code. Caregiver Social Workers will gather feedback from caregivers, including identifying additional health and wellbeing guidance that caregivers would find useful. KidsHealth are supportive of developing further health and wellbeing content where needed. This is the first phase of the development of guidance under the health focus areas under the Oranga Tamariki Action Plan. Additional guidance will be developed to support the redesigned Gateway service and enhances visibility of children in care within the health system. This will include guidance for frontline health professionals and Oranga Tamariki kaimahi.
Access to Primary Health Services and Dental Care | 2023-11-01 | Improvements are needed to the monitoring of data on PHO enrolments and annual health and dental checks. | Implement Frontline Technology Systems Upgrade, commencing July 2023, and including migration of CYRAS to an improved platform | Incremental release over 2024/25 and 2025/26 financial years | On track |  | Requirements have been gathered related to meeting the needs of health and dental information recorded and monitored by Oranga Tamariki.
Access to Primary Health Services and Dental Care | 2023-11-01 | There are opportunities for Oranga Tamariki to share information with health providers to improve access to primary health care | Consider formalising the sharing of data on a more frequent basis to both support individual children, and improve overall understanding of health experiences for tamariki and rangatahi in care | No completion date provided | On track |  | The health agencies are committed to sharing health information with Oranga Tamariki, and have been engaging with Oranga Tamariki to implement bidirectional data sharing to support tamariki and rangatahi access to health services to ensure their health needs are being met. Engagement is now focused on progressing an information sharing agreement between Oranga Tamariki and Te Whatu Ora and determining initial data shares regarding GP/PHO enrolment, immunisation status and engagement with an oral health provider.
Access to Primary Health Services and Dental Care | 2023-11-01 | Better implementation and oversight across Oranga Tamariki is needed. | Work with health agencies to develop a work programme for improved access to primary care and oral health | The next stage is expected to be completed by end of October 2024 | Not on track |  | The Gateway Assessment Review has been completed and Ministers for Children, Health, and Education have approved its findings and recommendations of six key changes for a redesigned Gateway service. These changes would shift the service from a one-off, specialist oriented approach to one which has an increased and ongoing role for primary healthcare, partners and providers, with regular review and ongoing support provided in a seamless and integrated way where children and whānau/family are at the centre of decision-making. A clearer accountability framework and strengthened governance will support these changes. We have developed a cross-agency plan for the Gateway redesign phased based on the recommendations. Ministry of Health has put the Integrated Service Model project on hold.
Access to Primary Health Services and Dental Care | 2023-11-01 | Better implementation and oversight across Oranga Tamariki is needed. | Work with health to progress a new integrated service model to provide responsive and timely access to tamariki in care | No completion date provided | Not on track |  | No response from Oranga Tamariki
Note on D89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provided the same response for a separate finding
Note on D91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provided as a planned action for EoCA above
Note on D94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provided as a planned action for EoCA above
Note on F82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We will need to ask OT for an update on the ones that have 2024 completion dates to determine if they are still on track (At the time of receiving the response to our data request they were).
Note on F87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Oranga Tamariki have marked this as complete, however there response indicates, “This is a work in progress…”.
Note on F95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: May need amending following update to Minister in June 25

## Open Home Foundation
Report | Report year | Findings by Monitor | Responses from Open Home Foundation (Planned actions) | Completion due date (provided by Open Home Foundation) | Progress on actions (Not started, On track, Not on track, Complete, Discontinued) | Year ICM published action as complete [For ICM use only/not for publication]. | Comments (Open Home Foundation) [Not for publication]
EoCA | 2020/2021 | Gaps in monitored agency data limits our ability to fully understand how they are meeting their obligations under the NCS Regulations. | Improvements made to OSCAR (Case Management System) to increase scope and support ease of reporting |  | Complete | 2023/24 | We can make additional changes if required. Currently no additions are needed
EoCA | 2021/2022 | No finding specific to Open Home Foundation. | Continued to refine self-monitoring and data capturing in OSCAR |  | Complete | 2023/24 | We have implemented changes this month on how we record social work hours so we can understand more easily how time is spent.
EoCA | 2020/2021 | Self-monitoring of compliance with NCS Regulations needs to improve, so we can understand the quality of care and how to improve. | Continue to develop ‘Better Off’ survey data | 2024-11-01 | Complete | 2024 | We have continued to develop our annual survey questions to better align with NCS. We continue to evaluate how we can better capture Better Off data. OHF note that there will be an on-going review process around how and how often it collects this data.
EoCA | 2020/2021 | Self-monitoring of compliance with NCS Regulations needs to improve, so we can understand the quality of care and how to improve. | Hold fortnightly forums to upskill social workers on NCS requirements | 2024-10-31 | Complete | 2024 | Changed frequency to monthly and added a monthly forum for Foster Parent Social Workers and their supervisors.
EoCA | 2021/2022 | No finding specific to Open Home Foundation. | Utilise ‘Better Off’ survey data for continuous improvement | Ongoing from 1 July 2024 | On track |  | Used Better Off data to supplement ongoing continuous improvement dicusssions to address practice issues.
EoCA | 2021/2022 | No finding specific to Open Home Foundation. | Continue to hold internal practice forums with a focus on the NCS Regulations | 2024-10-31 | Complete |  | Changed frequency to monthly and added a monthly forum for Foster Parent Social Workers and their supervisors.
EoCA | 2021/2022 | For social workers to successfully perform their role they need to be able to spend more time with tamariki, rangatahi, whānau, caregivers and communities. | Twelve month focus on increasing visits to tamariki, rangatahi, whānau carers and foster parents | Ongoing from 1 July 2024 | On track |  | We have continuted to see improvement in this area. We will do policy work around support to those who are approaching permanency as this is where we have seen visits to children drop while waiting for CoCA procedings.
EoCA | 2022/2023 | Social workers are not able to see tamariki and rangatahi as often as they need. | Visit frequency will be monitored by bi-monthly progress reporting | Ongoing from 1 July 2024 | On track |  | This work will continue. In 2023/2024, bi-monthly reports were developed to monitor visit frquency and identify areas to be addressed as they occurred.
EoCA | 2020/2021 | Connections with whānau and culture are important for tamariki and rangatahi Māori in care. | Te Roopu Māori kaimahi are supporting kaimahi to support tamariki and rangatahi Māori to be better connected to their whānau, hapū and Iwi | Ongoing from 1 July 2024 | On track |  | We have added a new position from Te Roopū to support this.
EoCA | 2020/2021 | Connections with whānau and culture are important for tamariki and rangatahi Māori in care. | Changes to be made in OSCAR to reflect work in te ao Māori |  | Complete |  | OSCAR has been adapted.
EoCA | 2020/2021 | Connections with whānau and culture are important for tamariki and rangatahi Māori in care. | Grow relationships with iwi/Māori organisations | Ongoing from 1 July 2024 | On track |  | This work continues, it has been a highlight to build connections with Kokiri Marae this year. We will contine to look for opportunities to collaborate.
EoCA | 2021/2022 | When staff lack cultural competence, relationships between Oranga Tamariki, whānau and other organisations can be negatively impacted. | Trialled a cultural plan based on Te Aho Takitoru framework to meet cultural needs of tamariki and rangatahi |  | Complete |  | This has been implemented.
EoCA | 2021/2022 | When staff lack cultural competence, relationships between Oranga Tamariki, whānau and other organisations can be negatively impacted. | Increased focus on connecting tamariki and rangatahi with their whānau and where they come from | Ongoing from 1 July 2024 | On track |  | More rangatahi have been supported to learn and visit where they are from, this work is continuing.
EoCA | 2020/2021 | Tamariki and rangatahi do not know and understand their rights. | Roll out a communication tool that will give tamariki and rangatahi an extra way to express their views |  | Complete |  | Mind of My Own continues to be available for tamariki and rangatahi in care. All new practice staff are trained in how to use this.
EoCA | 2021/2022 | To support tamariki and rangatahi to express their opinions, be involved in decisions, and share concerns, they need to know their rights. | Increase use of Mind of my Own app to engage tamariki and rangatahi in conversations and planning about them | 2025-10-01 | On track |  | This continues to be promoted by uptake remains a challenge particularly for our rangatahi. A review about its effectiveness will take place this year.
EoCA | 2021/2022 | To support tamariki and rangatahi to express their opinions, be involved in decisions, and share concerns, they need to know their rights. | Focus on tamariki having child-friendly plans | 2025-06-30 | Not on track |  | While changes have been implemented in the past year, improvement is slow. This led to further changes to OSCAR. A new system change went into OSCAR in June, we will continue to report on this and take into regional ARA forums. Staff were provided training in June and July on this.
EoCA | 2022/2023 | Tamariki and rangatahi are more involved in decisions about them | Ensure social workers are aware of policy expectations | 2025-06-30 | On track |  | This is ongoing and is discussed in service centre group supervision.
EoCA | 2022/2023 | Tamariki and rangatahi are more involved in decisions about them | Conduct 6 monthly progress checks (continuous improvement team) | 15 November 2024 (but will continue 6 monthly) | On track |  | Checks were done, but only resulted in slight improvement will monitor the implementation of the June changes.
EoCA | 2020/2021 | Caregivers need more support. | Caregivers receive on-going supervision and visits from their social workers |  | On track |  | We will continue bi-monthly reporting on this. Our executive team is going to explore ways in which we can build Foster Parent Social Worker capacity in regions where visits are particularly low, such as explore options of bring in trainers and extra Social Work hours. Over the last 6 months we have seen an increase in the amount of support our dedicated after hours team has provided to Foster Parents.
EoCA | 2020/2021 | Caregivers need more support. | Foster Parent Support Plan developed based on needs of tamariki and rangatahi |  | Complete | 2023/24
EoCA | 2020/2021 | Caregivers need more support. | Continue to provide Foster Parents with induction training, and introduction to trauma informed practice and additional online training | 2025-06-30 | On track |  | Ongoing, we will develop more online content with a Foster Parent/Whānau carer session with a particular focus on rangatahi.
EoCA | 2021/2022 | The prevalence of disability among tamariki in care is not well understood. | Disability advisors are active in their input into plans for disabled tamariki and rangatahi, and/or those with high needs | Ongoing from 1 July 2022 | On track |  | We can see evidence of Trauma and Disability Advisor support for Tamariki in OHF custody. Continuous Improvement Team will work with the Trauma and Disability Advisors to have up to date reports on Tamariki in care who have disability needs to ensure oversight of these Tamariki
EoCA | 2022/2023 | Allegations of abuse are not consistently recorded, and more support is needed following allegations. | Expectations of social workers when an allegation of abuse of neglect is made have been clarified in policies | 2024-11-15 | Complete | 2024 | Policy is clear, we aim to work with our Practice Managers on care concerns - things that are happening in placements that might be an indicator of concerns, that do not meet the tarrif of being an allegation. For the purposes of support teams to do case consults and increase support.
EoCA | 2022/2023 | Allegations of abuse are not consistently recorded, and more support is needed following allegations. | Allegations are flagged in OSCAR and elevated to a relevant senior manager | Ongoing from 1 July 2019 | On track |  | This continues to happen.

## Barnardos
Report | Report year | Findings by Monitor | Responses from Barnardos (Planned actions) | Completion due date (provided by Barnardos) | Progress on actions (Not started, On track, Not on track, Complete, Discontinued) | Comments (Barnardos) [Not for publication]
EoCA | 2020/2021 | Gaps in monitored agency data limits our ability to fully understand how they are meeting their obligations under the NCS Regulations. | Develop a self-monitoring tool |  | Complete
EoCA | 2020/2021 | Gaps in monitored agency data limits our ability to fully understand how they are meeting their obligations under the NCS Regulations. | Utilise self-audit tool |  | Complete | Self audit tool in place 2021. On-going monitoring of the use of QA tools from 2021.
EoCA | 2021/2022 | When staff lack cultural competence, relationships between Oranga Tamariki, whānau and other organisations can be negatively impacted. | Strengthen connections with local iwi to enable whanaungatanga with the foster care team and caregivers | Ongoing from 2021 | On track | Ongoing from start date 2021
EoCA | 2021/2022 | When staff lack cultural competence, relationships between Oranga Tamariki, whānau and other organisations can be negatively impacted. | Practice guidance is under development as part of strategic plan |  | Complete | Practice guidance completed 2022 - ongoing embedding to support kaimahi, and monitoring effectiveness from start date 2022.
EoCA | 2020/2021 | Agency support of health needs, especially mental health needs, is variable. | Develop a financial template to ensure tamariki and rangatahi do not experience funding barriers to accessing services |  | Complete

## Ministry of Education
Report | Report year | Findings by Monitor | Responses from Ministry of Education (Planned actions) | Completion due date (provided by the Ministry of Education) | Progress on actions (Not started, On track, Not on track, Complete, Discontinued) | Comments (Ministry of Education) [Not for publication]
EoCA | 2022/2023 | Collaboration and information sharing between government agencies remains a barrier. | Define and formalise good practice demonstrated in Ministry’s regional offices for wider use | Completion date not provided | Ongoing | Te Mahau have designed a new operating model that includes expectations to strengthen collaboration and information sharing between agencies, schools and regions. We have a dedicated team in Te Pae Aronui, Sector Change and Implementation, who have a strategic planned approach. The Ministry of Education’s change process is nearing completion. Staff have accepted roles across the organisation. MoE roles incorporate expertise in its structure. The planned action will build internal capability and further support. The Sector Change and Implementation approach supports clear and deliberate information sharing with MoE staff and schools.
|  |  | Actively connect Information sharing specialists with the Regions, providing support to help lift confidence and maturity when sharing information. Including when, how and to whom | Completion date not provided | Ongoing
EoCA | 2022/2023 | Collaboration and information sharing between government agencies remains a barrier. | Establish an Information Sharing Agreement (ISA) between the Ministry of Education and Oranga Tamariki | 2024/25 | On track | The ISA was signed in August 2024. The Agreement establishes ongoing information sharing of enrolment and attendance information for care experienced children and young people. Additionally, it provides the foundation for further discussions on information sharing that will contribute to understanding how to better improve the educational experiences of care experienced children and young people.The Government has set out six key priorities in 2024 to improve achievement. These include: • Targeted effective learning support. • Better use of data, assessment, and evidence to identify and invest in supports and services that work. There are work programmes underway to deliver these priorities and reach our achievement target. This work is underpinned by priorities across Attendance which work in synergy with Achievement. For example, the first Cross Agency Meeting has set work to review current information sharing in place. The Ministry has established a range of round table groups across the regions. These groups combine people from MoE, OT and other agencies. They meet to discuss matters pertaining to student need and develop a shared response. This is a link to the most recent attendance target report on the DPMC website.
EoCA | 2022/2023 | Access to education support continues to be a challenge. | Review how schools are resourced for teacher aides | 2023/24 | Complete | The Sector Reference Group was appointed to review the resourcing system and completed their review. Subsequently a new Minister was appointed with the change in Government in December 2024. The review was sent to the Minister of Education in mid-2024. The Minister is considering if and how she will take the review forward.
EoCA | 2022/2023 | Access to education support continues to be a challenge. | Support the review of Gateway Assessments and Student Aide Support under OTAP | 2023/24 | Complete | Officials from Oranga Tamariki, the Ministry of Health and the Ministry of Education are developing and costing redesign options. Understanding education needs and responses is a priority for the Ministry of Education within this redesign

## Health New Zealand
Report | Report year | Findings by Monitor | Responses from Ministry of Health/Health NZ (Planned actions) | Completion due date (provided by Health New Zealand) | Progress on actions (Not started, On track, Not on track, Complete, Discontinued) | Comments (Ministry of Health / Health NZ) [Not for publication]
EoCA | 2022/2023 | Access to health services continues to be a challenge. | Develop a joint outcomes framework to guide work supporting the mental health needs of tamariki with Oranga Tamariki engagement |  | Discontinued | A joint outcomes framework was developed to final draft stage in 2023 but has not been progressed since the change of government, with Ministers wanting to focus on a small set of specific pieces of work. Health agencies and Oranga Tamariki continue to work closely together to grow our mutual understanding of the mental wellbeing needs of this cohort. In 2024 a mental health work programme was added to the Oranga Tamariki Action Plan, alongside the other, broader, health actions in that Plan.
EoCA | 2022/2023 | Access to health services continues to be a challenge. | Ministers for Children, Health and Education agreed to complete a review of Gateway in 2023 as part of OTAP | Early 2024 | Complete | Work has proceeded during 2024 looking at options for a redesign of the Gateway service.
Access to Primary Health Services and Dental Care | 2023-11-01 | Policies and guidance are unclear, resulting in inconsistencies around caregiver responsibilities and health-related information being shared. | Work to improve health related information and guidance available for social workers and caregivers [with KidsHealth] |  | On track | Oranga Tamariki and Health New Zealand have worked with KidsHealth to give frontline kamahi and caregivers access to health and wellbeing guidance through the Oranga Tamariki Practice Centre. Guidance will be developed to support the redesigned Gateway service and work to enhance the visibility of children in care within the health system. Oranga Tamariki can advise further on this.
Access to Primary Health Services and Dental Care | 2023-11-01 | Policies and guidance are unclear, resulting in inconsistencies around caregiver responsibilities and health-related information being shared. | Explore opportunities to reduce barriers to parents and caregivers participation in discharge planning [with Oranga Tamariki] |  | Discontinued | Work with Oranga Tamariki to explore opportunities to address operational, practical, communication or training impediments for parents and caregivers involved in discharge planning has not progressed. Instead, health agencies and Oranga Tamariki have focused on a small set of specific pieces of work following Ministerial direction such as the redesign of Gateway.
Access to Primary Health Services and Dental Care | 2023-11-01 | Improvements are needed to the monitoring of data on PHO enrolments and annual health and dental checks. | Complete in-depth needs assessments to build evidence base of the primary health needs of children and young people in care |  | Complete | Published in 2024.
Access to Primary Health Services and Dental Care | 2023-11-01 | Improvements are needed to the monitoring of data on PHO enrolments and annual health and dental checks. | Establish cross-agency group to improve systematic use of data, evidence and insights between health and Oranga Tamariki |  | Complete | Group was established in 2023, has been on hold during the second part of 2024 due to significant changes in personnel at all agencies. This group will be reformed in 2025 as change processes are completed. A related piece of work looking at enhancing the visibility of children in care within the health system (sometimes referred to as identifiability) will also be looking to address the issues in this area.
Access to Primary Health Services and Dental Care | 2023-11-01 | There are opportunities for Oranga Tamariki to share information with health providers to improve access to primary health care. | Review the gateway assessment to identify opportunities for assessing health needs more effectively |  | Complete | MoH provided this response to EoCA and the health and dental review - the updates from MoH has been copied here.
Access to Primary Health Services and Dental Care | 2023-11-01 | Better implementation and oversight across Oranga Tamariki is needed. | Progress work on designing a new integrated service model to support responsive and timely access to primary health care for children in care |  | Discontinued | This project was deprioritised following the change in government, with Ministers wanting to focus on a small set of specific pieces of work. Work looking at a redesign of Gateway has taken priority in this space, and could be viewed as the first part of a wider effort to build a more integrated system between the different agencies to support children in care.